## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to the Project - Detailed | MUST HAVE | N/A | Dinesh Kumar | 3- Completed
S2 | S2 | US-002 | Project Workflow Explaination | MUST HAVE | N/A | Dinesh Kumar | 3- Completed
S3 | S3 | US-003 | Project Documentation Discussion (Agile Document) | MUST HAVE | N/A | Dinesh Kumar | 3- Completed
S4 | S4 | US-004 | Collection of Dataset (Images) | MUST HAVE | N/A | Dinesh Kumar | 3- Completed
S5 | S5 | US-005 | OCR Integration and discussion | MUST HAVE | Tesseract | Dinesh Kumar | 3- Completed
S6 | S6 | US-006 | Pre-processing the dataset (images) | MUST HAVE | Pytesseract | Dinesh Kumar | 3- Completed
S7 | S7 | US-007 | Visualization of processed data | MUST HAVE | Matplotlib | Dinesh Kumar | 3- Completed
S8 | S8 | US-008 | LLM model integration | MUST HAVE | PyTorch | Dinesh Kumar | 3- Completed
S9 | S9 | US-009 | Data Acquisition via Api | MUST HAVE | Flask | Dinesh Kumar | 3- Completed
S10 | S10 | US-010 | Design User Interface (UI) | MUST HAVE | Gradio | Dinesh Kumar | 3- Completed
S11 | S11 | US-011 | Data Acquisition via Web Scrapping | MUST HAVE | Beautifulsoup | Dinesh Kumar | 3- Completed
S12 | S12 | US-012 | Final Code Completion Ensuring Seamless Inegration | MUST HAVE | VsCode | Dinesh Kumar | 3- Completed
S13 | S13 | US-013 | Testing and Deployment | MUST HAVE | Gradio | Dinesh Kumar | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 40 | 7 | 6 | 7 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T ID-01 | Introduction to the Project - Detailed | 2025-02-07 | 2025-02-07 | Dinesh Kumar | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T ID-02 | Project Workflow Explaination | 2025-02-08 | 2025-02-08 | Dinesh Kumar | Design | 3- Completed | 3 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T ID-03 | Project Documentation Discussion (Agile Document) | 2025-02-09 | 2025-02-09 | Dinesh Kumar | Others | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T ID-04 | Collection of Dataset (Images) | 2025-02-10 | 2025-02-11 | Dinesh Kumar | Others | 3- Completed | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T ID-05 | OCR Integration and discussion | 2025-02-12 | 2025-02-13 | Dinesh Kumar | Integration Test | 3- Completed | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T ID-06 | Pre-processing the dataset (images) | 2025-02-13 | 2025-02-14 | Dinesh Kumar | Unit Test | 3- Completed | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T ID-07 | Visualization of processed data | 2025-02-17 | 2025-02-18 | Dinesh Kumar | Coding | 3- Completed | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T ID-08 | LLM model integration | 2025-02-18 | 2025-02-19 | Dinesh Kumar | Coding | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T ID-09 | Data Acquisition via Api | 2025-02-19 | 2025-02-20 | Dinesh Kumar | Integration Test | 3- Completed | 3 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T ID-10 | Design User Interface (UI) | 2025-02-20 | 2025-02-21 | Dinesh Kumar | Design | 3- Completed | 5 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T ID-11 | Data Acquisition via Web Scrapping | 2025-02-21 | 2025-02-22 | Dinesh Kumar | Coding | 3- Completed | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T ID-12 | Final Code Completion Ensuring Seamless Inegration | 2025-02-24 | 2025-02-28 | Dinesh Kumar | System Test | 3- Completed | 5 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T ID-13 | Testing and Deployment | 2025-03-01 | 2025-03-12 | Dinesh Kumar | System Test | 3- Completed | 4 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 03 | installing difficulties Tresseract | Conducted meeting to define and document clear worlflow processes
S6 | Day 06 | Difficulty for text extracting from structured documents | Implemented additional preprocessing techniques
S8 | Day 10 | Challenges with LLM model | Optimized the model
S9 | Day 12 | Difficulty in data acquisition via Bank API due to privacy issues | Adhering to the bank policy extracted data which is easily available
S5 | Day 14 | Difficulty in fine tuning due to complexity | Shifted to diltil bert instead of bart
S12 | Day 25 | Difficulty in integrating the codes | Conducted code review sessions to ensure seamless integration
S13 | Day 34 | Error and bugs faced during the deployment of app | Testing and monitoring to identify and resolve deployment issues

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7