## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Guru Prasad Naidu | 2025-02-12 | Error with OCR text extraction accuracy | S6 | Guru Prasad Naidu | Bugs | Adopted Pre-processing techniques | 2025-02-14 | Closed | Improve the accuarcy
2 | Guru Prasad Naidu | 2025-02-19 | Error with llm model fine-tuning | S8 | Guru Prasad Naidu | Logical | Utilized distilled versions for better performace | 2025-02-19 | Closed | Improved performance

## Sheet2
Logical
User Interface
Maintainability
Standards
Others